## Start Here
Project Management Dashboard - Simple Model
A light tracker for project leads who want a clear view of readiness, control, and delivery confidence without managing a heavy PMO workbook.
How to use it
1) Replace the example rows on the Projects sheet with your own active projects or workstreams.
2) Use 1-5 scores for the health measures. Keep them honest and discussion-oriented rather than over-engineered.
3) Use the Risks & Issues sheet only if you want a light RAID-style view alongside the headline project tracker.
4) Review the Dashboard monthly or fortnightly to identify which projects need sponsor attention, tighter controls, or clearer scope.

## Projects
Project Tracker
Replace the example rows. Blue cells = inputs. Black cells = formulas.
Project ID | Project / programme | Sponsor | Project lead | Objective summary | Priority (1-5) | Scope clarity (1-5) | Plan quality (1-5) | Resource confidence (1-5) | Governance quality (1-5) | Delivery control (1-5) | Overall delivery readiness | Current status | Next milestone | Target end date | Notes
PM-001 | CRM implementation | COO | J. Patel | Launch CRM with phased migration and adoption plan | 5 | 4 | 4 | 3 | 4 | 3 | 3.6 | Active | Confirm data migration cutover | 2026-06-30
PM-002 | Factory line optimisation | Operations Director | C. Weber | Improve throughput and reduce downtime | 5 | 3 | 3 | 4 | 3 | 3 | 3.2 | Active | Approve vendor timeline | 2026-08-15
PM-003 | HR operating model redesign | CHRO | N. Evans | Simplify HR processes and service model | 4 | 4 | 3 | 3 | 4 | 3 | 3.4 | Planning | Lock design principles | 2026-09-01
PM-004 | Nonprofit donor system upgrade | CEO | A. Gomez | Replace legacy donor platform with lower manual effort | 3 | 3 | 2 | 2 | 3 | 2 | 2.4 | Watch | Clarify resourcing gap | 2026-07-31

## Risks & Issues
Risks & Issues (optional)
Use this only if you want a simple view of the main blockers without maintaining a full RAID log.
Project ID | Risk / issue | Type | Severity (1-5) | Likelihood (1-5) | Owner | Mitigation / next action | Due date | Status | Notes
PM-001 | Data cleansing behind plan | Risk | 4 | 4 | J. Patel | Add dedicated data owner and weekly review | 2026-04-10 | Open
PM-002 | Vendor slot may slip | Risk | 4 | 3 | C. Weber | Escalate installation timing with sponsor | 2026-04-05 | Open
PM-004 | No confirmed business analyst support | Issue | 5 | 5 | A. Gomez | Approve interim contractor or reduce scope | 2026-03-28 | Open

## Dashboard
Project Portfolio Dashboard
This summary is designed for monthly or quarterly review.
Average overall delivery readiness | 3.15 |  | Scores closer to 5.0 suggest stronger delivery discipline.
Average plan quality | 3 |  | Low scores often mean timelines are not yet credible.
Average resource confidence | 3 |  | Useful for spotting hidden delivery risk.
Active projects | 2 |  | Watch projects often need management attention too.
Rank | Project | Lead | Priority | Readiness | Status
1 | CRM implementation | J. Patel | 5 | 3.6 | Active
2 | HR operating model redesign | N. Evans | 4 | 3.4 | Planning
3 | Factory line optimisation | C. Weber | 5 | 3.2 | Active
4 | Nonprofit donor system upgrade | A. Gomez | 3 | 2.4 | Watch

## Glossary
Glossary
Term | Meaning | Practical note
Scope clarity | Whether the team is clear on what is in, out, and why. | Low scores usually cause rework later.
Plan quality | How credible and sequenced the plan is. | Ask whether milestones and dependencies are believable.
Resource confidence | Confidence in people, time, and capability. | Useful as an early warning indicator.
Governance quality | Quality of sponsor engagement, decision-making rhythm, and escalation. | Low scores often slow delivery even when the team is capable.
Delivery control | Whether risks, issues, decisions, and status are actively controlled. | A good indicator of project discipline.
Overall delivery readiness | Average of scope clarity, plan quality, resource confidence, governance quality, and delivery control. | Good for comparing projects at a glance.