## Start Here
Project Management Dashboard - Advanced Model
A structured model for project and programme teams that want to separate plan quality, execution health, risk pressure, governance quality, and delivery confidence across a portfolio.
How to use it
1) Start on Projects and create one row per active project, programme, or workstream.
2) Use Workstreams for the main phases or work packages. Use RAID for the real risks, issues, assumptions, and decisions that could move the project outcome.
3) Use Dependencies and Decisions to capture the cross-functional or sponsor actions that often create delay.
4) Use Status Log for periodic health updates; review the Scorecard and Dashboard monthly or fortnightly.

## Settings
Settings and scoring assumptions
Metric weight | Value | Use | Score band | Meaning
Plan quality | 0.25 | Credibility of work plan | 4.2 - 5.0 | Strong
Execution health | 0.25 | Progress against commitments | 3.4 - 4.1 | Generally solid
Risk control | 0.2 | Inverse of risk pressure | 2.6 - 3.3 | Mixed
Governance quality | 0.15 | Decision quality and escalation | 1.8 - 2.5 | Fragile
Delivery confidence | 0.15 | Management judgement | <1.8 | Critical

## Projects
Projects - one row per active project
Blue cells are inputs. Black cells calculate from other sheets. Replace the example rows.
Project ID | Project / programme | Sponsor | Project lead | Objective summary | Current phase | Priority (1-5) | Review month | Plan quality score | Execution health score | Risk pressure score | Governance quality score | Delivery confidence score | Weighted delivery score | Priority-adjusted score | Overall status | Management note | Next governance ask
PJ-001 | CRM implementation | COO | J. Patel | Launch CRM with phased migration and adoption plan | Build | 5 | 2026-03 | 3.5 | 3 | 4 | 2.5 | 3 | 2.85 | 2.85 | Mixed |  | Approve cutover governance
PJ-002 | Factory line optimisation | Operations Director | C. Weber | Improve throughput and reduce downtime | Implementation | 5 | 2026-03 | 3 | 3 | 4 | 3 | 3 | 2.8 | 2.8 | Mixed |  | Resolve vendor timing
PJ-003 | HR operating model redesign | CHRO | N. Evans | Simplify HR processes and service model | Design | 4 | 2026-03 | 4 | 4 | 3 | 4 | 4 | 3.8 | 3.04 | Mixed |  | Lock target-state decisions

## Workstreams
Workstreams - main phases or work packages
Use this sheet to make the plan visible. Add only the workstreams that matter for management review.
Project ID | Workstream | Owner | Stage | Milestone date | Status | Completion % | Plan quality score (1-5) | Comment | Dependency note
PJ-001 | Data migration | J. Patel | Build | 2026-04-20 | Amber | 40 | 3 | Cleansing behind plan | Awaiting source-system owners
PJ-001 | Training & adoption | PMO | Design | 2026-05-10 | Green | 20 | 4 | Outline ready
PJ-002 | Vendor installation | C. Weber | Implementation | 2026-04-30 | Amber | 35 | 3 | Slot timing unclear | Depends on shutdown window
PJ-003 | Target operating model | N. Evans | Design | 2026-04-15 | Green | 50 | 4 | Decision pack in progress

## RAID
RAID - risks, issues, assumptions, decisions
This is the main pressure log. Keep it focused on items that could materially change project delivery.
Project ID | Item ID | RAID type | Description | Impact (1-5) | Risk pressure (1-5) | Status | Owner | Mitigation / next action | Due date
PJ-001 | R-001 | Risk | Data quality from legacy systems is weaker than assumed | 5 | 4 | Open | J. Patel | Add cleansing lead and weekly report | 2026-04-05
PJ-002 | R-002 | Risk | Vendor slot may slip by two weeks | 4 | 4 | Open | C. Weber | Escalate decision on shutdown window | 2026-03-29
PJ-003 | I-001 | Issue | Design principles not yet signed off | 4 | 3 | Open | N. Evans | Sponsor workshop to confirm trade-offs | 2026-03-27

## Dependencies
Dependencies - cross-functional dependencies worth managing
Track only the dependencies that can move timing, scope, or confidence materially.
Project ID | Dependency | Depends on who / what | Needed by | Current status | Resolution confidence (1-5) | Owner | Next action | Notes
PJ-001 | Source system extracts | IT operations | 2026-04-01 | At risk | 2 | J. Patel | Escalate extract ownership
PJ-002 | Shutdown window approval | Plant leadership | 2026-03-28 | Pending | 3 | C. Weber | Confirm decision in ops review
PJ-003 | Policy design sign-off | HR leadership team | 2026-03-26 | On track | 4 | N. Evans | Prepare sponsor options

## Decisions
Decisions - capture the decisions that unblock delivery
Use this to make decision quality and sponsor responsiveness visible.
Project ID | Decision needed | Decision owner | Decision date needed | Current status | Decision quality / clarity (1-5) | Governance quality score (1-5) | Owner | Notes
PJ-001 | Approve migration cutover approach | COO | 2026-04-08 | Pending | 4 | 3 | J. Patel | Decision paper in draft
PJ-002 | Confirm shutdown window | Operations Director | 2026-03-29 | Pending | 3 | 3 | C. Weber | Timing drives vendor slot
PJ-003 | Approve target-state design principles | CHRO | 2026-03-27 | Scheduled | 4 | 4 | N. Evans | Workshop booked

## Status Log
Status Log - periodic health check
Use one row per project per reporting period so trends are visible over time.
Project ID | Review date | Schedule status | Budget / effort status | Execution health score (1-5) | Delivery confidence score (1-5) | Top update | Owner
PJ-001 | 2026-03-15 | Amber | Green | 3 | 3 | Migration tasks behind plan but controls improved | J. Patel
PJ-002 | 2026-03-15 | Amber | Amber | 3 | 3 | Vendor timing risk unresolved | C. Weber
PJ-003 | 2026-03-15 | Green | Green | 4 | 4 | Design phase progressing as planned | N. Evans

## Scorecard
Monthly project scorecard
This is the management view. It mirrors the main calculated fields from Projects and adds a simple rank.
Rank | Project ID | Project | Lead | Status | Plan quality | Execution health | Risk pressure | Governance quality | Delivery confidence | Priority-adjusted score
2 | PJ-001 | CRM implementation | J. Patel | Mixed | 3.5 | 3 | 4 | 2.5 | 3 | 2.85
3 | PJ-002 | Factory line optimisation | C. Weber | Mixed | 3 | 3 | 4 | 3 | 3 | 2.8
1 | PJ-003 | HR operating model redesign | N. Evans | Mixed | 4 | 4 | 3 | 4 | 4 | 3.04

## Dashboard
Advanced Project Dashboard
This summary is designed for monthly or quarterly review.
Average weighted delivery score | 3.15 |  | Base delivery strength before priority adjustment.
Average priority-adjusted score | 2.9 |  | Useful for sponsor attention and PMO review.
Average risk pressure | 3.67 |  | Higher values mean more unresolved pressure.
Projects in strong / generally solid status | 0 |  | Quick read on portfolio resilience.
Rank | Project | Lead | Priority-adjusted score | Status | Next governance ask
1 | HR operating model redesign | N. Evans | 3.04 | Mixed | Lock target-state decisions
2 | CRM implementation | J. Patel | 2.85 | Mixed | Approve cutover governance
3 | Factory line optimisation | C. Weber | 2.8 | Mixed | Resolve vendor timing

## Glossary
Glossary
Term | Meaning | Practical note
Plan quality score | Credibility of milestones, sequencing, and work package design. | If low, fix the plan before adding pressure to the team.
Execution health score | How well the project is progressing against near-term commitments. | Use as the core operating signal.
Risk pressure score | How much unresolved risk or issue pressure is sitting on the project. | Higher means worse; the weighted model inverts it.
Governance quality score | Whether sponsor engagement, escalation, and decisions are strong enough. | Often the hidden reason delivery drifts.
Delivery confidence score | Management judgement on whether the project can still deliver from here. | Use as synthesis, not as the only evidence.