## Start Here
Public Affairs Impact Dashboard - Advanced Model
A structured model for public affairs teams that want to separate engagement quality, narrative traction, stakeholder movement, outcome movement, confidence, and file priority.
How to use it
1) Start on Files and create one row per active file, issue, campaign, or policy priority.
2) On Objectives, define what success looks like for each file and weight those objectives so they total 100 per File ID.
3) Use Stakeholders for the institutions, officials, coalitions, and third parties that materially affect results. Use Engagements only for meaningful interventions.
4) Use Signals & Outcomes and Evidence to make movement and confidence explicit rather than relying on volume alone.
5) Review the Scorecard and Dashboard monthly; use them for management decisions, not just reporting.

## Settings
Settings and scoring assumptions
Leave this sheet unchanged unless you want to change the model weights.
Metric weight | Value | Use | Confidence score | Multiplier | Meaning
Engagement quality | 0.2 | Quality of meaningful public affairs interventions | 1 | 0.7 | Weak evidence
Narrative traction | 0.2 | Whether your frame is showing up in policy debate or stakeholder feedback | 2 | 0.8 | Some signal
Stakeholder movement | 0.25 | Movement among priority stakeholders and institutions | 3 | 0.9 | Reasonable evidence
Outcome movement | 0.35 | Progress against weighted objectives | 4 | 1 | Good evidence
Total weight |  | Should total 1.00 | 5 | 1.1 | Strong evidence / triangulation

## Files
Files - one row per active file, campaign, or issue
Blue cells are inputs. Black cells calculate from other sheets. Replace the example rows.
File ID | File / issue / campaign | Owner | Function / market | Objective summary | Current stage | Priority (1-5) | Review month | Engagement quality score | Narrative traction score | Stakeholder movement score | Outcome movement score | Confidence score | Weighted impact score | Priority-adjusted score | Overall status | Management note | Next 30-day priority
F-001 | Packaging regulation file | A. Smith | EU Public Affairs | Protect recycled-content pathway in final text | Final negotiation | 5 | 2026-03 | [8 empty] | Coalition broadly aligned; opposition narrative tightening | Secure compromise text with rapporteur
F-002 | Hospital funding campaign | R. Khan | Health advocacy | Win regional budget support for new oncology unit | Committee review | 5 | 2026-03 | [8 empty] | Clinician support improving but budget headroom still tight | Lock finance committee champion
F-003 | SME tax reform file | L. Chen | Trade association | Obtain phased implementation and guidance note | Draft legislation | 5 | 2026-03 | [8 empty] | Business coalition aligned, ministry still cautious | Shift treasury concern from timing to safeguards
F-004 | Data centre permitting programme | M. Rossi | Corporate affairs | Reduce local objections and speed up permit path | Local hearings | 3 | 2026-03 | [8 empty] | Supportive business voices emerging; environmental criticism remains active | Turn mitigation package into planning consent language
F-005 | Skills levy reform file | J. Walker | Employer coalition | Secure apprenticeship flexibility in levy redesign | Consultation window | 4 | 2026-03 | [8 empty] | Officials are engaging substantively; provider concerns need bridging | Submit revised drafting with provider cover
F-006 | Climate disclosure implementation | S. Dubois | Financial services PA | Win transition relief and pragmatic supervisory guidance | Regulatory guidance | 4 | 2026-03 | [8 empty] | Industry ask coherent; supervisors open but non-committal | Convert technical ask into supervisor-ready options

## Objectives
Objectives - define what success looks like
Add specific outcomes for each file. The objective weights should total 100 for each File ID.
File ID | Objective / outcome | Weight (%) | Current status | Movement score (1-5) | Why this score? | Owner | Due date | Objective category | Notes
F-001 | Preserve recycled-content pathway in compromise text | 40 | Partially achieved | 4 | Draft language still intact in working text | A. Smith | 2026-04-12 | Legislative text
F-001 | Prevent a hard cap on transitional exemptions | 35 | In progress | 3 | Council side remains split on implementation timing | A. Smith | 2026-04-18 | Legislative text
F-001 | Hold cross-party support for industry amendment | 25 | Mostly achieved | 4 | Key moderate group still backing compromise | A. Smith | 2026-04-05 | Stakeholder coalition
F-002 | Regional finance committee backs capital allocation | 45 | In progress | 4 | Chair is supportive but wants stronger utilisation evidence | R. Khan | 2026-04-09 | Budget decision
F-002 | Clinician coalition sustains public support | 30 | Mostly achieved | 4 | Senior clinicians are now speaking consistently in favour | R. Khan | 2026-04-01 | Coalition building
F-002 | Draft budget note includes oncology unit wording | 25 | Partially achieved | 3 | Drafting discussion has started but not yet locked | R. Khan | 2026-04-15 | Budget text
F-003 | Treasury accepts phased implementation principle | 40 | In progress | 3 | Officials recognise the operational risk of immediate rollout | L. Chen | 2026-04-14 | Policy design
F-003 | Revenue agency commits to guidance note | 35 | At risk | 2 | Agency still resisting a formal guidance commitment | L. Chen | 2026-04-20 | Implementation
F-003 | Business coalition remains aligned on messaging | 25 | Mostly achieved | 3 | Core members aligned but regional chambers need reassurance | L. Chen | 2026-04-07 | Coalition management
F-004 | Planning committee proceeds without deferment | 35 | In progress | 3 | Officers have not recommended delay but objections remain active | M. Rossi | 2026-04-03 | Permitting process
F-004 | Local business voices outnumber organised objections | 35 | Mostly achieved | 4 | Chamber and suppliers now publicly supportive | M. Rossi | 2026-04-10 | Third-party advocacy
F-004 | Mitigation package is accepted as credible | 30 | Partially achieved | 3 | Noise and traffic package viewed as serious but incomplete | M. Rossi | 2026-04-18 | Mitigation package
F-005 | Consultation reflects employer flexibility ask | 40 | Mostly achieved | 4 | Officials are testing language close to the coalition proposal | J. Walker | 2026-04-08 | Consultation response
F-005 | Training providers support amendment package | 30 | In progress | 3 | Most providers supportive if quality safeguards are explicit | J. Walker | 2026-04-16 | Stakeholder support
F-005 | Ministerial office requests revised drafting option | 30 | Mostly achieved | 4 | Office asked for revised wording after follow-up meeting | J. Walker | 2026-04-05 | Political engagement
F-006 | Supervisor indicates phased implementation is plausible | 40 | In progress | 3 | Supervisory team is open but wants stronger comparability evidence | S. Dubois | 2026-04-11 | Regulatory guidance
F-006 | Trade body note adopts proportionality framing | 30 | Mostly achieved | 4 | Association note now mirrors the proportionality language | S. Dubois | 2026-04-06 | Narrative traction
F-006 | Firms align on common technical ask | 30 | Mostly achieved | 4 | Largest firms have converged on a shared transition proposal | S. Dubois | 2026-04-09 | Industry alignment

## Stakeholders
Stakeholders - weighted movement tracker
Track only the institutions, officials, coalitions, or third parties that materially affect the file.
File ID | Stakeholder / institution / coalition | Role / type | Influence (1-5) | Previous position / openness (1-5) | Current position / openness (1-5) | Weighted current score | Movement vs previous | Owner | Next action | Notes | Relationship quality (1-5)
F-001 | EU Parliament rapporteur | Decision-maker | 5 | 3 | 4 |  |  | A. Smith | Share compromise drafting note | Open to technical fixes if coalition stays unified | 4
F-001 | Council attaché group | Civil service | 4 | 2 | 3 |  |  | A. Smith | Provide implementation risk memo | Several capitals still cautious on exemptions | 3
F-001 | NGO recycling coalition | Third party | 4 | 3 | 4 |  |  | A. Smith | Offer joint roundtable on integrity safeguards | Tone improved after technical briefing | 4
F-002 | Regional finance committee chair | Decision-maker | 5 | 3 | 4 |  |  | R. Khan | Equip chair with utilisation and waiting-list data | Supportive but needs fiscal narrative | 4
F-002 | Clinician coalition | Third party | 4 | 3 | 4 |  |  | R. Khan | Coordinate op-ed and testimony timing | Now visibly aligned on campaign ask | 4
F-002 | Health ministry budget unit | Civil service | 3 | 2 | 3 |  |  | R. Khan | Send capital expenditure options paper | Still cautious on precedent risk | 3
F-003 | Treasury tax directorate | Civil service | 5 | 2 | 2 |  |  | L. Chen | Stress compliance risk of immediate go-live | Concerned about perceived delay | 2
F-003 | Revenue agency implementation team | Civil service | 4 | 2 | 3 |  |  | L. Chen | Share business process map and guidance draft | Technical engagement improved slightly | 3
F-003 | SME coalition leads | Industry coalition | 4 | 3 | 3 |  |  | L. Chen | Hold coalition alignment call | Supportive but impatient | 4
F-004 | Planning committee members | Decision-maker | 5 | 2 | 3 |  |  | M. Rossi | Run site visit with mitigation experts | Still mixed but less oppositional than last month | 3
F-004 | Local chamber of commerce | Third party | 4 | 3 | 4 |  |  | M. Rossi | Activate supplier and jobs case studies | Now advocating publicly for timetable certainty | 4
F-004 | Residents association | Community group | 4 | 1 | 2 |  |  | M. Rossi | Offer targeted traffic and noise workshop | Opposition remains but tone is less confrontational | 2
F-005 | Skills ministry officials | Civil service | 5 | 3 | 4 |  |  | J. Walker | Submit revised drafting with implementation guardrails | Officials engaging on detailed text | 4
F-005 | Training provider federation | Third party | 4 | 2 | 3 |  |  | J. Walker | Co-design quality safeguards | Support improving if misuse concerns are addressed | 3
F-005 | Employer coalition steering group | Industry coalition | 4 | 4 | 4 |  |  | J. Walker | Keep members aligned on fallback asks | Alignment strong and disciplined | 5
F-006 | Supervisory policy team | Regulator | 5 | 2 | 3 |  |  | S. Dubois | Provide scenario analysis on transition relief | Listening closely but not yet committed | 3
F-006 | Banking association | Industry coalition | 4 | 3 | 4 |  |  | S. Dubois | Coordinate joint technical annex | Now echoing proportionality framing | 4
F-006 | Finance ministry sustainable finance desk | Civil service | 4 | 3 | 4 |  |  | S. Dubois | Link relief request to market stability narrative | More receptive after bilateral discussion | 4

## Engagements
Engagements - log only meaningful interventions
This is not a contact database. Log only engagement that could plausibly improve narrative traction, stakeholder movement, or outcome progress.
File ID | Date | Engagement type | Audience / target | Objective of engagement | Asset / evidence used | Observed immediate effect | Timeliness (1-5) | Relevance (1-5) | Engagement quality score | Owner | Notes
F-001 | 2026-03-04 | Technical briefing | EU Parliament rapporteur | Protect compromise drafting | Legal drafting note + implementation examples | Requested redline text for trilogue prep | 5 | 5 |  | A. Smith
F-001 | 2026-03-11 | Coalition roundtable | NGO recycling coalition | Stabilise credibility narrative | Lifecycle evidence pack | Coalition accepted integrity safeguards language | 4 | 4 |  | A. Smith
F-002 | 2026-03-05 | Committee prep meeting | Regional finance committee chair | Strengthen capital allocation case | Utilisation and waiting-list data | Chair asked for two additional local case studies | 5 | 4 |  | R. Khan
F-002 | 2026-03-13 | Clinician media prep | Clinician coalition | Keep external narrative disciplined | Patient outcomes briefing pack | Coalition adopted common top lines for interviews | 4 | 4 |  | R. Khan
F-003 | 2026-03-06 | Treasury bilateral | Treasury tax directorate | Reduce resistance to phased implementation | Operational readiness memo | Officials accepted need to test transition options | 3 | 4 |  | L. Chen
F-003 | 2026-03-14 | Coalition alignment call | SME coalition leads | Hold common message and fallback asks | Draft guidance proposal | Members stayed aligned but requested firmer timelines | 3 | 3 |  | L. Chen
F-004 | 2026-03-07 | Community briefing | Residents association | Lower objections before hearings | Noise and traffic mitigation pack | Questions became more technical and less adversarial | 4 | 3 |  | M. Rossi
F-004 | 2026-03-12 | Business roundtable | Local chamber of commerce | Mobilise supportive third-party voices | Jobs and tax contribution note | Chamber offered two public advocates for hearing | 4 | 4 |  | M. Rossi
F-005 | 2026-03-08 | Official workshop | Skills ministry officials | Advance drafting on levy flexibility | Alternative drafting options | Officials requested revised wording and safeguard examples | 5 | 4 |  | J. Walker
F-005 | 2026-03-15 | Provider consultation | Training provider federation | Reduce concern over quality dilution | Safeguards slide deck | Providers agreed to review compromise language | 4 | 4 |  | J. Walker
F-006 | 2026-03-09 | Regulatory technical session | Supervisory policy team | Make transition relief credible | Scenario analysis + peer examples | Supervisors asked for narrower calibration options | 4 | 4 |  | S. Dubois
F-006 | 2026-03-16 | Association working group | Banking association | Align industry ask | Technical annex draft | Association agreed to circulate joint annex | 4 | 5 |  | S. Dubois

## Signals & Outcomes
Signals & Outcomes - make movement explicit
Use this sheet for material policy, political, media, or stakeholder signals that tell you whether the case is landing.
File ID | Date | Item / signal | Signal type | Tone / favourability (1-5) | Stakeholder relevance (1-5) | Narrative traction (1-5) | Outcome signal (1-5) | Why this matters | Owner
F-001 | 2026-03-12 | Rapporteur office feedback note | Political signal | 4 | 5 | 4 | 4 | Shows the compromise route remains live if technical safeguards hold | A. Smith
F-001 | 2026-03-18 | Coalition statement after roundtable | Third-party signal | 4 | 4 | 4 | 3 | Supportive tone reduced reputational attack surface | A. Smith
F-002 | 2026-03-10 | Regional paper editorial | Media signal | 4 | 4 | 3 | 4 | Editorial framed the oncology unit as a service resilience investment | R. Khan
F-002 | 2026-03-17 | Committee member feedback | Political signal | 4 | 5 | 4 | 4 | Two undecided members shifted toward the capital allocation case | R. Khan
F-003 | 2026-03-11 | Treasury meeting readout | Policy signal | 3 | 5 | 3 | 3 | Officials acknowledged implementation risk but kept fiscal caution | L. Chen
F-003 | 2026-03-19 | Trade association newsletter pickup | Stakeholder signal | 3 | 4 | 2 | 2 | The phased approach landed internally but not yet with government audiences | L. Chen
F-004 | 2026-03-13 | Local hearing preview article | Media signal | 3 | 4 | 3 | 3 | Coverage balanced economic benefits with continuing local objections | M. Rossi
F-004 | 2026-03-20 | Chamber endorsement letter | Third-party signal | 4 | 4 | 4 | 3 | Provides credible local economic support ahead of hearings | M. Rossi
F-005 | 2026-03-14 | Departmental readout | Policy signal | 4 | 5 | 4 | 4 | Officials asked for revised wording rather than rejecting the ask | J. Walker
F-005 | 2026-03-21 | Provider federation comment | Stakeholder signal | 4 | 4 | 4 | 3 | Public comment signalled conditional support for compromise | J. Walker
F-006 | 2026-03-18 | Supervisor follow-up email | Regulatory signal | 4 | 5 | 4 | 3 | Signals willingness to examine calibrated relief options | S. Dubois
F-006 | 2026-03-22 | Association note to members | Industry signal | 4 | 4 | 3 | 3 | Proportionality framing is now sticking across the sector | S. Dubois

## Evidence
Evidence - record why you believe your work mattered
Use this to make confidence explicit. If the evidence base is thin, the model should show that.
File ID | Evidence item | Evidence type | Confidence score (1-5) | What does this support? | Source / link | Date | Owner | Notes
F-001 | Tracked redline retains recycled-content pathway | Document | 4 | Outcome movement | Negotiation tracker | 2026-03-18 | A. Smith
F-001 | Coalition statement mirrors agreed safeguard framing | Triangulated signal | 5 | Narrative traction + stakeholder movement | Roundtable outputs | 2026-03-18 | A. Smith
F-002 | Committee chair requested local proof points rather than challenging the core ask | Meeting note | 4 | Outcome movement | Chair meeting note | 2026-03-05 | R. Khan
F-002 | Clinician coalition spokespeople used common campaign language | Triangulated signal | 4 | Narrative traction | Media prep notes | 2026-03-13 | R. Khan
F-003 | Treasury acknowledged operational risk in bilateral readout | Meeting note | 3 | Outcome movement | Bilateral note | 2026-03-11 | L. Chen
F-003 | Coalition maintained common fallback position | Document | 3 | Stakeholder movement | Coalition minutes | 2026-03-14 | L. Chen
F-004 | Chamber endorsement letter committed to speaking at hearing | Document | 4 | Stakeholder movement | Chamber letter | 2026-03-20 | M. Rossi
F-004 | Residents association questions shifted from principle to mitigation detail | Observed signal | 3 | Engagement quality | Community briefing note | 2026-03-07 | M. Rossi
F-005 | Ministerial team requested revised drafting after workshop | Meeting note | 4 | Outcome movement | Workshop note | 2026-03-08 | J. Walker
F-005 | Provider federation comment accepted the safeguards frame | Triangulated signal | 5 | Narrative traction + stakeholder movement | Federation note | 2026-03-21 | J. Walker
F-006 | Supervisor asked for narrower calibration options rather than rejecting relief | Meeting note | 4 | Outcome movement | Technical session note | 2026-03-09 | S. Dubois
F-006 | Association note adopted proportionality framing across member firms | Document | 4 | Narrative traction | Association circular | 2026-03-22 | S. Dubois

## Scorecard
Monthly file scorecard
This is the management view. It mirrors the main calculated fields from Files and adds a simple rank.
Rank | File ID | File / issue | Owner | Status | Engagement quality | Narrative traction | Stakeholder movement | Outcome movement | Confidence | Priority-adjusted score

## Dashboard
Advanced Public Affairs Dashboard
This summary is designed for monthly or quarterly review.
Average weighted impact score |  |  | Base outcome-oriented score before priority adjustment.
Average priority-adjusted score |  |  | Useful for deciding where management attention belongs.
Average narrative traction |  |  | Low scores usually mean the case is not landing clearly enough.
Files in strong / generally solid status |  |  | Quick read on portfolio resilience.
Rank | File | Owner | Priority-adjusted score | Status | Next 30-day priority

## Glossary
Glossary
Term | Meaning | Practical note
Engagement quality score | Quality of meaningful public affairs interventions logged on the file. | Use to challenge busy but weak engagement patterns.
Narrative traction score | Whether the intended frame is showing up in policy debate, stakeholder feedback, or external signals. | If this is low, revisit the case, proof points, or messengers.
Stakeholder movement score | Movement among priority officials, institutions, coalitions, and third parties. | Treat as a leading indicator, not final proof of impact.
Outcome movement score | Progress against the weighted objectives you defined at the start. | Keeps the file anchored in explicit outcomes.
Confidence score | How strong the evidence is that your team's work contributed to the movement observed. | Separating confidence from impact reduces over-claiming.